## Sheet1
Tasks | Date of completion | Comments
Process flow as per the slide before , no more repeated rows in the emails | 18th March
Source Onboarding form | takes 1 man day(Backend) | Completion date depends on frontend completion as they need to consume API
Alerts Configuration Form | takes 2 man days(Backend) | Completion date depends on frontend completion as they need to consume API
Redundancy logic : Headline match for the last 7 days | 18th March | Development is done we are into testing phase for this
Email syntax | 19th March - 20th March | Will be taken after row 2 is completed
Event Alert Email : Subscribe to a type of alerts from UI and get an alert | 21st March - 25th March
Query in RDBMS to find the ‘impacted supplier’ and the corresponding open Pos (BE) | 26th March - 28th March
Query in RDBMS for selecting the impacted OU corresponding to the ‘impacted supplier’ (BE)
Query in RDBMS to get the supplier supplying the same item as the ‘impacted supplier’ (DS, BE)
Integration, testing, adhoc tasks | No ETA